## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2211-swen-261-04-b
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | TL; 10/4/21; "sign in" button displayed in nav-bar on home page
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | TL; 10/4/21;
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | TL; 10/4/21
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | TL; 10/4/21
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | TL; 10/4/21
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | TL; 10/4/21
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | TL; 10/4/21
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | TL; 10/5/21
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | TL; 10/5/21
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | TL; 10/5/21
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | TL; 10/5/21
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | TL; 10/5/21
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | TL; 10/5/21
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | TL; 10/5/21
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | TL; 10/5/21
As a player I want to take turns with my opponent so that my opponent doesn’t get more moves than me. | Given it is my turn to move when I make my move then I expect that my turn will end, and my opponent's turn will begin. | Pass | TL; 10/26/21
| Given it is my opponent turns to move when they make a move then I expect that their turn will end, and my turn will begin. | Pass | TL; 10/26/21
| Given that it is my turn when my opponent attempts to make a move, then I expect their move to be rejected. | Pass | TL; 10/26/21
| Given that it is my opponents turn when I attempt to make a move, then I expect my move to be rejected. | Pass | TL; 10/26/21
As a player I want the red checker to go first so that the gameplay between red/white remains consistent with real life checkers. | Given that a game has started when the game is loaded then the red player will go first | Pass | TL; 10/26/21
As a player I want each team's starting checkers to be at their end of the board so my opponent won’t get a head start. | Given that a game has started when the game loads then I expect that the proper alignment of an American Checker Board is shown | Pass | TL; 10/26/21
As a player I want a player to win, given that either someone lost all their checkers or can no longer move, so that games can be completed. | Given I am in a game of checkers, when I run out of pieces, then I expect to lose the game. | Pass | TL; 11/3/21
| Given I am in a game of checkers, when my opponent runs out of pieces, then I expect to win the game. | Pass | TL ; 11/3/21
| Given that I am in a game, when someone wins, then I expect to be moved back to the Home page | Pass | TL; 11/3/21; Home page accessed by hitting the quit button for both the winner and the loser
As a player I should be able to jump over my opponent’s checkers to eliminate them, so I can take down my opponent and win the game. | Given that there is an opportunity to jump over an opponent's piece, when it's my turn, then I expect to jump over their piece and eliminate it | Pass | TL; 11/3/21
As a player I want my opponent to be forced to jump over me if he can, so that I can pressure him into losing valuable pieces on the board. | Given that there is an opportunity to jump over an opponent's piece, when it's my turn, then I expect to jump over their piece and eliminate it | Pass | TL; 11/3/21
As a player I want non-promoted checkers to only be able to move forward, so that my opponent can’t undo their moves. | Given that I have a non-promoted checker, when I attempt to move backward, then I expect the move to be refused. | Pass | TL; 11/3/21
As a player I want to be able to jump over multiple opponent checkers at a time, given that I am jumping over an opponent checker each time, so I can heavily punish my opponent when he is exposed. | Given that I have an opportunity for a multi-jump, when I jump, then I expect for the multi-jump to occur. | Pass | TL; 11/3/21
As a player I want the opponent to be forced to complete a multi-jump, so that I may plan accordingly to where the checker will be heading based on it. | Given that I have an opportunity for a multi-jump, when I jump, then I expect for the multi-jump to occur. | Fail | TL; 11/3/21; Multi-Jumps are currently implemented but not forced
As a player I want my checker to be promoted to a King, given that it reaches the end of the board, so I can get kings for myself. | Given I am playing a game, when one of my pieces reaches the end of the board, then I expect that that piece gets promoted to a King Piece | Pass | TL; 11/3/21
As a player I want the king to be able to move forwards and backwards, so that I can use its powers to my advantage. | Given I have a piece that is a King, when I drag and drop the King piece, then I expect the piece to have valid moves going both forward and backwards | Pass | TL; 11/3/21
As a player I want Kings to be visually different from normal checkers, so that I can track them on the board easily. | Given that I have a piece that is a King, when I look at that piece, then I expect the piece to appear visually different so that I can differentiate it from normal pieces | Pass | TL; 11/3/21
As a Player I want there to be a visible forfeit button on my screen during the game so I can quit it whenever I want to. | Given I am in a game, when I look at the view, then there should be a button that say resign on the screen | Pass | TL; 11/3/21
As a Player I want the opponent to win the game and quit upon me forfeiting, so that I can reward him for successfully beating me. | Given that I have clicked the resign button, when I have successfully resigned, then I expect the opponent to win. | Fail | TL; 11/3/21; Resign button needs further implementation
| Given that I have clicked the resign button, when I have successfully resigned, then I expect to be brought back to the home page. | Fail | TL; 11/3/21; Resign button needs further implementation
As a player I want to be able to select between being a player and spectator before a game starts, so that I can freely watch and play whenever I want. | Given I am signed in and at the home page when I see the page I expect to see a list of games being played so I could join to spectate them.
As a player I want to be able to view the past moves the competitors have played, so that I can see what moves have led to a certain moment in the game. | Given I am spectating a game when I push the back button, then I expect to see the previous moves played in the current game
Given I am spectating a game when I push the forwards button, then I expect to be brought to the current state of the game
As a player I want to be able to chat with other spectators so I can discuss what is currently going on during the game. | Given I am spectating a game when I see the game page then I expect their to be a chat box to communicate with others spectating
As a Player I want to be able to enable asynchronous play so that I can choose to continue playing a game whenever I choose | Given I am playing game, when I choose to leave the application for a period of time, then I should be able to rejoin my game from the home page
As a User I want to be able to receive a notification on my account when my opponent in an asynchronous game has made a move so that I am aware when I can make a move. | Given that I am playing a game but on the home page, when it is my turn to make a move, then I expect the application to notify me when I can make my move
Given that I received a notification, when I click the notification, I expect to be brought to the game that I am in
As a Player I want the system to automatically forfeit players from a game if they haven't moved in a while so I don't have to wait forever for them to make a turn. | Given I am playing a game, when my opponent leaves the application for a long period of time, then I expect them to be timed out and for me to win the game